## Estimates
Story Number | Epic | Story | Points | Estimated Hours | Completed | Completed Points | Completed Hours
1 | Project Setup | Information Architecture Diagram | 1 | 4 | TRUE | 1 | 4
2 | Project Setup | Define Roles | 1 | 4 | TRUE | 1 | 4
3 | Project Setup | Git Repository | 1 | 4 | TRUE | 1 | 4
4 | Project Setup | Visual Studio Solution | 1 | 4 | TRUE | 1 | 4
5 | Project Setup | AppVeyor Build Pipeline | 1 | 4 | TRUE | 1 | 4
6 | Project Setup | Static Code Quality Analysis | 1 | 4 | TRUE | 1 | 4
7 | Project Setup | Project Plan | 2 | 8 | TRUE | 2 | 8
8 | Project Setup | Implementation Plan | 2 | 8 | TRUE | 2 | 8
9 | Project Setup | Application Infrastructure Diagram | 1 | 4 | TRUE | 1 | 4
10 | Project Setup | Application Architecture Diagram | 1 | 4 | TRUE | 1 | 4
11 | Project Setup | Entity Relationship Diagram | 2 | 8 | TRUE | 2 | 8
12 | Project Setup | Admin Blazor Module | 1 | 4 | TRUE | 1 | 4
13 | Project Setup | Entity Framework | 2 | 8 | TRUE | 2 | 8
14 | Project Setup | Estimates | 1 | 4 | TRUE | 1 | 4
15 | Project Setup | Entity Framework Models | 2 | 8 | TRUE | 2 | 8
16 | Project Setup | Serilog Console, File Logging | 2 | 8 | TRUE | 2 | 8
17 | Project Setup | Create Theme Using Syncfusion Theme Studio for Blazor | 1 | 4 |  | 0 | 0
18 | Project Setup | Code Quality Check Razor Pages | 1 | 4 |  | 0 | 0
19 | Project Setup | Code Quality Check Async Methods | 1 | 4 | TRUE | 1 | 4
20 | Project Setup | Setup Deployment | 3 | 16 |  | 0 | 0
21 | Home Page | Home Page Header | 3 | 16 |  | 0 | 0
22 | Home Page | Image Rotator | 2 | 8 |  | 0 | 0
23 | Home Page | Home Page Middle | 2 | 8 |  | 0 | 0
24 | Home Page | Home Page Footer | 2 | 8 |  | 0 | 0
25 | Basic Administration | Login | 3 | 16 |  | 0 | 0
26 | Basic Administration | Logout | 2 | 8 |  | 0 | 0
27 | Basic Administration | Administration Dashboard | 3 | 16 |  | 0 | 0
28 | Basic Administration | Edit Configuration | 5 | 32 |  | 0 | 0
29 | Basic Administration | Edit Home Page | 5 | 32 |  | 0 | 0
30 | Basic Administration | Edit Header | 5 | 32 |  | 0 | 0
31 | Basic Administration | Edit Footer | 5 | 32 |  | 0 | 0
32 | Manage Images and Videos | List Images and Videos | 5 | 32 |  | 0 | 0
33 | Manage Images and Videos | Upload Image | 3 | 16 |  | 0 | 0
34 | Manage Images and Videos | View Image | 2 | 8 |  | 0 | 0
35 | Manage Images and Videos | Delete Image | 2 | 8 |  | 0 | 0
36 | Manage Images and Videos | Rename Image | 2 | 8 |  | 0 | 0
37 | Manage Images and Videos | New Folder | 1 | 4 |  | 0 | 0
38 | Manage Web Pages | List Pages | 3 | 16 |  | 0 | 0
39 | Manage Web Pages | Add Page | 5 | 32 |  | 0 | 0
40 | Manage Web Pages | Edit Page | 2 | 8 |  | 0 | 0
41 | Manage Web Pages | Delete Page | 2 | 8 |  | 0 | 0
42 | Manage Web Pages | Rename Page | 2 | 8 |  | 0 | 0
43 | National Pages | National About Us Page | 2 | 8 |  | 0 | 0
44 | National Pages | National History of Bed Brigade Page | 2 | 8 |  | 0 | 0
45 | Locations | Location List | 3 | 16 |  | 0 | 0
46 | Locations | Grove City Location Home Page | 3 | 16 |  | 0 | 0
47 | Locations | Polaris Location Home Page | 3 | 16 |  | 0 | 0
48 | Locations | Bed Brigade Near Me | 5 | 32 |  | 0 | 0
49 | Locations | Grove City Assembly Instructions | 2 | 8 |  | 0 | 0
50 | Locations | Polaris Assembly Instructions | 2 | 8 |  | 0 | 0
51 | Locations | Grove City Partners | 2 | 8 |  | 0 | 0
52 | Manage Locations | Manage Locations Page | 5 | 32 |  | 0 | 0
53 | Manage Locations | Edit Location | 3 | 16 |  | 0 | 0
54 | Manage Locations | Add Location | 5 | 32 |  | 0 | 0
55 | Manage Locations | Deactivate/Activate Location | 2 | 8 |  | 0 | 0
56 | Location Request Bed | Request Bed Page | 5 | 32 |  | 0 | 0
57 | Location Request Bed | Manage Bed Requests | 5 | 32 |  | 0 | 0
58 | Location Request Bed | Schedule Deliveries | 5 | 32 |  | 0 | 0
59 | Location Request Bed | Delivery Checklist | 3 | 16 |  | 0 | 0
60 | Location Request Bed | Bulk Email Scheduled Deliveries | 5 | 32 |  | 0 | 0
61 | Location Volunteer | Volunteer Page | 5 | 32 |  | 0 | 0
62 | Location Volunteer | Manage Volunteers | 5 | 32 |  | 0 | 0
63 | Location Volunteer | Bulk Email Volunteers | 3 | 16 |  | 0 | 0
64 | Location Contact Us | Contact Us Page | 3 | 16 |  | 0 | 0
65 | Location Contact Us | Manage Contacts | 5 | 32 |  | 0 | 0
66 | Location Donations | Setup Paypal IPN | 5 | 32 |  | 0 | 0
67 | Location Donations | Grove City Donate | 3 | 16 |  | 0 | 0
68 | Location Donations | Polaris Donate | 3 | 16 |  | 0 | 0
69 | Location Donations | Manage Donations | 5 | 32 |  | 0 | 0
70 | Location Donations | Email Tax Forms | 5 | 32 |  | 0 | 0
71 | Manage Users | User List | 3 | 16 |  | 0 | 0
72 | Manage Users | Add User | 3 | 16 |  | 0 | 0
73 | Manage Users | Edit User | 3 | 16 |  | 0 | 0
74 | Manage Users | Delete User | 3 | 16 |  | 0 | 0
75 | National News | National News Sample Story | 3 | 16 |  | 0 | 0
76 | National News | List of News | 3 | 16 |  | 0 | 0
77 | National News | News Detail | 3 | 16 |  | 0 | 0
78 | National News | Add News | 3 | 16 |  | 0 | 0
79 | National News | Edit News | 3 | 16 |  | 0 | 0
80 | National News | Delete News | 2 | 8 |  | 0 | 0
81 | Location Stories | Grove City Sample Story | 2 | 8 |  | 0 | 0
82 | Location Stories | Polaris Sample Story | 2 | 8 |  | 0 | 0
83 | Location Stories | List of Stories | 2 | 8 |  | 0 | 0
84 | Location Stories | Story Detail | 2 | 8 |  | 0 | 0
85 | Location Stories | Add Story | 2 | 8 |  | 0 | 0
86 | Location Stories | Edit Story | 2 | 8 |  | 0 | 0
87 | Location Stories | Delete Story | 2 | 8 |  | 0 | 0
88 | Search | Search Indexing | 5 | 32 |  | 0 | 0
89 | Search | Search Bar | 3 | 16 |  | 0 | 0
90 | Search | Search Results | 5 | 32 |  | 0 | 0
91 | Advanced Features | Remove Image Geolocation | 2 | 8 |  | 0 | 0
92 | Advanced Features | Convert Image to WebP | 2 | 8 |  | 0 | 0
93 | Advanced Features | Page Versioning | 5 | 32 |  | 0 | 0
94 | Advanced Features | Page History | 5 | 32 |  | 0 | 0
95 | Advanced Features | Restore Version | 5 | 32 |  | 0 | 0
Total |  |  | 273 | 1480 |  | 23 | 92
Total Weeks | 46.25
Remaining Weeks of Work | 43.375
Week Number | 5
Estimated Completion Date | 2023-11-01 15:00
Average Points Completed Per Week | 4.6
Average Hours Completed Per Week | 18.4

## Points
Points | Complexity | Hours
1 | Dead Simple | 4
2 | Low | 8
3 | Medium | 16
5 | High | 32
8 | Too Complex, Break Up | 64

## Resources
Name | Dedicated Development Hours Per Week
Greg | 8
James | 4
Anna | 20
Total | 32

## Variables
Variable | Value
Start Date | 2022-11-27